## WBS with Gantt Chart
WORK BREAKDOWN STRUCTURE WITH GANTT CHART
PROJECT TITLE | [6 empty] | COMPANY NAME
PROJECT MANAGER | [6 empty] | DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception & Initiation
1.1 | Project Charter | Leon W | 2017-03-12 | 2017-03-15 | 4 | 100% | bar: WEEK 1 F to WEEK 2 F
1.1.1 | Project Charter Revisions | Kylie R | 2017-03-15 | 2017-03-16 | 2 | 100% | bar: WEEK 2 W to WEEK 2 F
1.2 | Research | Pete S | 2017-03-15 | 2017-03-21 | 7 | 90% | bar: WEEK 2 W to WEEK 3 R
1.3 | Projections | Steve L | 2017-03-16 | 2017-03-22 | 7 | 40% | bar: WEEK 2 W to WEEK 3 R
1.4 | Stakeholders | Allen W | 2017-03-17 | 2017-03-22 | 7 | 70% | bar: WEEK 2 W to WEEK 3 R
1.5 | Guidelines | Malik M | 2017-03-18 | 2017-03-22 | 7 | 60% | bar: WEEK 2 W to WEEK 3 R
1.6 | Project Initiation | Malik M | 2017-03-23 | 2017-03-23 | 1 | 50% | bar: WEEK 2 W to WEEK 2 F; WEEK 3 F
2 | Project Definition & Planning
2.1 | Scope & Goal Setting | Steve L | 2017-03-24 | 2017-03-28 | 5 | 5% | bar: WEEK 2 W to WEEK 2 F; WEEK 4 M to WEEK 4 F
2.2 | Budget | Allen W | 2017-03-29 | 2017-04-02 | 5 | 30% | bar: WEEK 2 W to WEEK 2 F
2.3 | Communication Plan | Malik M |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
2.4 | Risk Management | Malik M |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
3 | Project Launch & Execution
3.1 | Status & Tracking | Pete S |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
3.2 | KPIs | Leon W |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
3.2.1 | Monitoring | Kylie R |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
3.2.2 | Forecasts | Kylie R |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
3.3 | Project Updates | Pete S |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
3.3.1 | Chart Updates | Malik M |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
4 | Project Performance / Monitoring
4.1 | Project Objectives | Steve L |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
4.2 | Quality Deliverables | Allen W |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
4.3 | Effort & Cost Tracking | Malik M |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
4.4 | Project Performance | Malik M |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
CLICK HERE TO CREATE WBS TEMPLATES WITH GANTT CHART IN SMARTSHEET

## WBS with Gantt Chart BLANK
WORK BREAKDOWN STRUCTURE WITH GANTT CHART
PROJECT TITLE |  | Capstone Project |  |  |  |  | COMPANY NAME | [8 empty] | Meezy Cutz
PROJECT MANAGER |  | Ayman Ibrahim ; Kierra McCallum ; Zack Munford |  |  |  |  | DATE | [8 empty] | August 30th, 2017
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception & Inititation | Group | 2017-08-30 | TBA | N/A
1.1 | Requirements | Group | 2017-08-23 | 2017-08-30 | 1 week | 100%
1.2 | Projections | Group | 2017-08-30 | TBA | N/A | 0%
1.3 | [5 empty] | 0%
1.4 | [5 empty] | 0%
1.5 | [5 empty] | 0%
1.6 | [5 empty] | 0%
1.7 | [5 empty] | 0%
2 | Design and Implementation
2.1 | HTML |  |  |  |  | 0%
2.2 | CSS |  |  |  |  | 0%
2.3 | JavaScript |  |  |  |  | 0%
2.4 | Documentation |  |  |  |  | 0%
3 | Testing and Prototype
3.1 | [5 empty] | 0%
3.2 | [5 empty] | 0%
3.3 | [5 empty] | 0%
3.4 | [5 empty] | 0%
3.5 | [5 empty] | 0%
3.6 | [5 empty] | 0%
4 | Project Launch & Execution
| Monitoring |  |  |  |  | 0%
| Content Updates |  |  |  |  | 0%
| Media Updates |  |  |  |  | 0%
0%